## Slide 1
KICK-OFF MEETING
ARISE
Augmented Rehabilitation & Intelligent System for Enhancement
The first proactive "AI Coach" for Sit-to-Stand (STS) rehabilitation
Start Date:
June 18, 2026
Expected End:
December 18, 2027

## Slide 2
The Problem and the Vision
!
The Problem:
Discontinuity of care in motor rehabilitation (STS). Incorrect implementation at home and lack of objective data.
+
The Solution:
A product/service that acts as a "Virtual Therapist." Not just reactive estimation, but 3D measurement and proactive guidance (forecasting).
#
The 3 Pillars of ARISE:
1. Core AI (Measurement and Prediction)
2. "Coach" Edge Device
3. Clinical Cloud Dashboard
[Photo of patient + therapist]

## Slide 3
Project Objectives (TRL6)
*
Patients
Improve ADL and reduce fall risk by providing intuitive visual and auditory biofeedback, designed with low cognitive load.
*
Therapist
Provide an advanced decision dashboard based on objective kinematic data (not qualitative estimates) to personalise treatment plans.
*
Business (EaaS)
Validate the technology to launch the "Equipment as a Service" (EaaS) business model for clinics, nursing homes, and home tele-rehabilitation.

## Slide 4
★ Work and Development Plan (GANTT)
18-Month Roadmap: 18 June 2026 - 18 December 2027
T1 ('26)
T2 ('26)
T3 ('26/'27)
T4 ('27)
T5 ('27)
T6 ('27)
7
8
9
10
11
12
1
2
3
4
5
6
7
8
9
10
11
12
WP1: Project Mngt.
M1-M18 (Governance & Ethics)
WP2: Analysis & Architecture.
M2-M7 (Cloud & UX/UI)
WP3: AI & HW Research
M4-M11 (Dataset & Pose 3D)
Bridge (AI continuation)
M8-M18 (AI refinement during integration & validation)
WP4: Platform Dev
M9-M14 (Edge & Dashboard)
WP5: TRL6 Validation
M14-M18 (Real Environment Test)
D1.1
D1.2
D2.1
D3.1
D4.1
M5.1
T5.4
D5.1
D1.3

## Slide 5
★ Project Deliverables and Milestones List
Code
Title
Operational Description
Clinical Requirements and Biomechanical KPIs
Defines the scientific Ground Truth and the KPIs (angles, velocities) needed for AI training.
Submission to the Ethics Committee
Drafting of the clinical protocol, inclusion criteria, and formal submission for CER approval.
Final Report and Dissemination
Project management report and reporting of scientific dissemination activities carried out.
UI/UX Design (Mockup)
Creation and validation of visual prototypes for the patient (Biofeedback) and therapist (Dashboard) interfaces.
STS Dataset Acquisition and Annotation
Acquisition of STS recordings at the clinical site and DINOGMI-led double-blind annotation, building the AI training corpus.
AI Models and STS Datasets
Clinical data acquisition and training of algorithms for real-time 3D estimation and forecasting.
TRL6 Platform Prototype
Release of the Coach hardware device and cloud infrastructure, ready for the real world.
Cloud Platform Release
Cloud back-end, ingestion API, and Clinical Dashboard delivered as a separate release distinct from the Coach edge hardware.
Start of Trial (TRL6)
Clinical setup, patient recruitment, and official start of testing inside the gym.
AI vs. Gold Standard Comparison
Statistical analysis of AI metrics compared with laboratory optoelectronic systems (REHELAB).
TRL6 Validation Report
Final document on scientific validation, usability, patient adherence, and clinical impact.
Patient and Therapist Feedback Report
Intermediate usability and adherence report at the mid-point of WP5, feeding D5.1 with early signals.
D1.1
D1.2
D1.3
D2.1
T3.2
D3.1
D4.1
D4.2
M5.1
T5.4
D5.1
D5.2

## Slide 6
★ Focus Partner: University of Genoa (DINOGMI)
Role & Activities
Scientific Partner:
Member of the Biomechanical Validation Committee and definition of the Gold Standard at REHELAB.
Initial Phase:
Define the scientific Ground Truth (biomechanical KPIs) by mid-August 2026, and only then start drafting the Ethics Committee protocol, since the KPIs are what the trial measures.
Critical issues:
Slow approval by the Regional Ethics Committee, and KPI sign-off slipping past M3.
Mitigation:
Lock D1.1 KPIs by mid-August, then run protocol drafting and EC pre-submission in parallel from M3 to M4 to absorb committee review time.
ID
Deliverable / Activity
Expected Deadline
D1.1
Definition of Clinical Requirements and KPIs
Mid-August 2026
D1.2
Submission to the Ethics Committee
Mid-September 2026
T5.4
AI vs. Gold Standard Comparison
Mid-October 2027
D5.1
Final Report - Validation & Dissemination
18 December 2027

## Slide 7
Focus Partner: Buccarella Associates
Role & Activities
Clinical-Operational Partner:
Deputy for Real-World Validation.
Unlike the University, which deals with pure scientific validation, the Buccarella Studio provides the fundamental perspective of the real environment.
Critical issues:
Difficulty in recruiting patients during the months of WP5.
Mitigation:
Pre-screening and pre-enrollment in the months preceding the tests.
ID
Deliverable / Activity
Expected Deadline
D1.2
Workflow Protocol for the Ethics Committee
Mid-September 2026
D2.1
Feedback UI/UX - Biofeedback and Dashboard
Mid-November 2026
T3.2
STS Dataset Acquisition (clinical hosting)
M9 to M15
M5.1
Experimental Launch - TRL6 Test
Mid-September 2027
D5.1
Validation Report - Data and Adherence
18 December 2027

## Slide 8
★ Integrated Operational Contribution (UniGe & Buccarella)
ID
Deliverable
Expiration
UniGe Contribution (Scientific)
Studio Buccarella Contribution (Clinical)
D1.1
Clinical Requirements and KPIs
Mid-Aug '26
Defines the scientific Ground Truth and KPIs (angles, velocity) used to train the AI.
Supplies the functional and usability requirements of the patients.
D1.2
Ethics Protocol
Mid-Sep '26
Scientific and formal coordination for drafting the CER protocol, after D1.1 KPI sign-off.
Practical definition of patient inclusion criteria, logistics, and clinical workflow.
D2.1
Feedback UI/UX
Mid-Nov '26
Consulted on the clinical and scientific accuracy of the kinematic data shown in the mockups.
Tests intuitiveness of biofeedback for elderly patients and usefulness of the dashboard.
T3.2
STS Dataset Acquisition
M9 to M15
Methodological supervision of the acquisition and DINOGMI-led ground-truth annotation.
Provides the clinical site, patients, and healthy volunteers for the recordings.
M5.1
Setup Startup (TRL6)
Mid-Sep '27
Methodological supervision of the setup to ensure the validity of the data in the environment.
Patient recruitment, consent management, and session management.
T5.4
AI vs. Gold Std
Mid-Oct '27
Statistical comparison of ARISE measurements vs the REHELAB optoelectronic Gold Standard.
Provides field clinical logs to support and explain any detected anomalies.
D5.1
TRL6 Final Report
18 Dec '27
Final scientific validation, statistical analysis, academic paper writing.
Data on patient adherence, practical usability, impact on workload.

## Slide 9
★ RACI Matrix of Clinical Activities and Validation
ID
Deliverable / Activity
Innovina S.r.l.
UniGe (DINOGMI)
Studio Buccarella
Clinical Requirements and Biomechanical KPIs
Protocol and Submission to the Ethics Committee
Feedback UI/UX (Mockup Coach & Dashboard)
STS Dataset Acquisition and Annotation
Patient Trial Setup and Startup (TRL6)
AI Data Comparison vs. Gold Standard
TRL6 Final Validation Report
D1.1
A
R
C
D1.2
A
R
R
D2.1
A/R
C
C
T3.2
A
C
R
M5.1
A
R
R
T5.4
A
R
I
D5.1
A/R
R
R
R
Responsible — physically carries out the work
A
Accountable — approves and has final responsibility
C
Consulted — provides essential input
I
Informed — kept informed of progress

## Slide 10
★ Strategic Alignment & Risk Management
CRITICAL MILESTONE: TRL6 PROTOTYPE DEPLOYMENT (M14 to M18)
Platform availability: Mid-August 2027 (M14) | First patient: Mid-September 2027 (M15) | AI vs Gold Std: Mid-October 2027 (M16) | Final report: 18 December 2027 (M18)
Compressed window: 4 months from platform availability to final report. Risk of recruitment / analysis spillover, mitigated by pre-screening from M11 and a 2-month D5.2 interim report (mid-November 2027).
Guide Questions for DINOGMI
Ethical Bureaucracy:
What are the worst-case timelines for the CER? Given the protocol drafting starts after KPI sign-off at M3, what is the plan B if approval slips past M6?
AI Feasibility:
How do we ensure that the desk-defined biomechanical KPIs (D1.1) can be robustly extracted from markerless sensors?
Bridge Phase:
During the Bridge phase (M8 to M18), how do we coordinate AI iteration with WP4 integration and WP5 validation so that issues found in the trial can be triaged without invalidating it?
Guide Questions for Buccarella Studio
Patient Recruitment:
Given a 4-month WP5 window (M14 to M18), what is a realistic estimate of eligible patients enrollable, and when should pre-screening start (M11?)
Workflow Integration:
What is the maximum acceptable time (minutes) to start the Coach in the gym, so as not to hinder the therapists?
Geriatric Usability:
How do we calibrate biofeedback (visual/auditory) to stimulate self-correction without frightening or confusing an elderly patient?

## Slide 11
★ Next Steps (First 30-60 Days)
1
Formal Kick-Off Setup
Project management tools and document-sharing setup by Innovina. 18-month GANTT alignment (Start: 18 June 2026).
2
Technical Tables - KPI Definition
Immediate and priority launch of technical tables (Innovina & DINOGMI) for the drafting of D1.1 (Clinical Requirements and Biomechanical KPIs).
3
Ethics Committee Protocol (sequenced)
Joint Innovina-DINOGMI-Buccarella drafting of the Clinical Protocol starts only AFTER D1.1 KPI sign-off (mid-August 2026), to avoid drafting in the dark. EC pre-submission window M3 to M4.
4
Design Startup (WP2)
Launch of cloud architecture and UI/UX analysis, gathering initial clinical feedback on user interaction and dashboard needs.